**Project Charter**

**Project Title**

**The Impact of Part-Time Employment on Academic Performance and Health Among University Students**

**Members**

* IT23226814 – Vakesh R
* IT23195752 – Salah I
* IT23286382 - Jayakody D T
* IT23279070 - Samarajeewa B G D M M

**Project Overview**  
This project aims to explore the relationship between part-time employment, academic performance, and health among students at SLIIT (Sri Lanka Institute of Information Technology). The focus is on identifying behaviours associated with effective work-life-study balance and understanding why some students struggle academically due to part-time jobs.

**Project Objectives**

1. To collect responses from SLIIT students who are engaged in part-time jobs.
2. To understand the characteristics of students who successfully balance work, life, and study.
3. To identify factors contributing to academic challenges among students with part-time jobs.
4. To present insights and recommendations based on the findings.

**Data to be Collected**:

* Demographic Information:

Age, Gender, Year of Study, Faculty, Field of Study

* Part-Time Job Details:

Employment Status, Job Type, Work Hours, Reason for Working, Job Duration

* Academic Performance:

Current GPA, Study Hours, Class Attendance, Previous Average GPA, Perceived Impact, Support from University

* Extracurricular Activities:

Participation, Types of Activities, Time Commitment

* Health:

Sleep Hours, Health Impacts

**Methodology**: A questionnaire will be developed to gather the above information from SLIIT students, focusing particularly on 3rd and 4th-year students. The collected data will be categorized and analysed using statistical techniques to identify trends and insights.

The SLIIT students who are doing part time jobs are the population for this analysis and the group of students who are going to respond our survey is the sample.

**Project Timeline**:

* Week 2: Finalize questionnaire and distribute to target students.
* Weeks 3-4: Data collection phase.
* Week 5: Preliminary data analysis and review.
* Week 6: Detailed data analysis and insights development.
* Weeks 7-10: Preparation of presentation.
* Week 13: Final presentation.

**Communication Plan**:

* Weekly team meetings to monitor progress.
* Continuous updates through whatsapp group.